## Sheet1
Risk Detail | Probability (Low, Medium, High) | Impact (Low, Medium, High) | Effect on project | Risk Reduction Actions | Actions (if happens)
Loss of key staff | L | H | unable to complete key features | motivate staff, emphasis of importance of project keep architecture changes to a minimum preemptively hire new staff for pair programming ensure documentation and work records are available at any time | divert existing resources, hire replacements
Architecture changes | L | H | Time and quality cost | ensure requirements are well investigated | discuss impact of change and implement if agreed in key staff
Key staff time available not meeting the demands of project | M | H | unable to complete key features | reuse available open source software preemptively hire new staff for pair programming | beg for mercy/more time
Hardware losses/data corruption | L | L | Time and quality cost | automate deployment of key components make sure the deployment system is functional ensure sources/modifications are always saved to a cloud enabled service (github) | rewrite lost code
Poor intra project communication | M | M | Disjointed work, time and quality cost | propose weekly face to face meetings daily stand up remote meeting for quick status updates | keep a longer face to face meeting to sync issues
Unable to write portable code for device cloud client | L | H | Unable to run project on a certain device platform | ensure that the build process compiles for MIPS and ARM besides x86/ia64 | investigate availability of specific platform toolchain/BSP/SDK
Used server side components are hard to integrate | M | M | Time and quality cost | early in the project star prototyping a simple components interoperability | use the existing staff resources to work on this specific problem issue postponing current development
Project is useless compared to competition - cloud | M | H | wasted resources | Many competing implementations | Make framework more lightweight than enterprise implementations - easier to pick up by potential users
Project is useless compared to competition - voting | L | H | wasted resources | The only competition is pnyx | Find feature that pnyx does not offer - for example, due to the distributed nature we can have voters express preferences while aggregation nodes or results computation nodes aren't available.
Sophistication of users - cloud | L | M | hinders adoption | The target for the cloud framework is other developers, who can be assumed to be technically sophisticated | Still, have decent documentation or the target market won't bother considering us
Sophistication of users - voting | H | M | hinders adoption | Anyone can be called to vote - see political elections. | Voter facing components should be as easy to use as possible.
Project staff size |  |  | limited scope with only two people | acquire more staff | really acquire more staff
Collaboration resources unavailable | VL | H | unable to collaborate - but are google docs and github ever going to close during our lifetimes? | keep offline backups, keep alternative solutions in mind | switch to azure, bitbucket etc